## Slide 1: BLD Project

## Slide 2
Teem members :
Mostafa Ashraf Ali Ahmed
Mostafa Mahmoud Mohamed Khalifa
Mahmoud Mohamed Ahmad Mohamed
Mariam Maher
Mariam Gap Allah Aziz
Supervisor
Alaa Abdel Fattah
Doctor :
Ibrahim Al-Awadi
Project management

## Slide 3: Project Identification ::
 | Project identification
(BLD) Blood | Name
To solve the problem of blood shortage in hospitals and provide the necessary blood for patients | Description
Ministry of Health, Red Crescent. | Sponsor
Eng. Alaa Abdel Fattah | Project Manger

## Slide 4: Business Case
(BLD) Blood app is a mobile app designed to be connected with hospital needed blood and donor , the user will use the app to donate blood, by entering his name ,phone number, blood type and location waiting message from any hospital nearby him , when hospital need blood for patient admin user for hospital enter how much he need and type blood , app send message to all users have the needed blood type to go to the hospital that needs to donate blood .

## Slide 5: Project scope:
Version (1.0.0)…..will provide an appropriate blood donators by :
(scope statement) ….. The project will be completed and approval for testing in three months at ASSUIT University Hospital (ALKASR) such as beginning at a cost not to exceed 100,000 $ .
Phase one team of android developer , team connectes the servers in hospitals and collecting data .
The app will be written in java because the purpose of app is searching on appropriate donators .
Project exclusions::
System maintenance and repair will be done only up to three months after .
Tasks defined for version 1.1.0

## Slide 6
Frontend
Data base
gathering info from ministry of health and hospital
Backend
Integration
Reserve a server in Google cloud
Design UI/UX
Develop
Test
Testing
Coding
Full Testing
BLD.App

## Slide 7
Responsible matrix
Activates | Mostafa Khalifa | Mostafa El Shahaby | Mahmoud Wahman | Mariam Gappla | Mariam Maher
Gathering information from MOH | C | I | A | C | R
Gathering information from hospital | I | C | I | R | A
Reserve a server in google cloud | I | A | R | I | C
Design | R | I | C | I | C
Develop | I | A | C | R | I
Test | A | R | I | C | I
Coding | C | I | A | R | C
Testing | R | C | I | A | C
Full Test | I | A | R | A | C
R: Responsible C: Consulted I: Informed A: Acountable

## Slide 8
0 | A | 1
0 |  | 0
0 | 1 | 1
0 | B | 1
0 |  | 0
0 | 1 | 1
1 | E | 6
1 |  | 1
2 | 5 | 7
3 | D | 7
0 |  | 0
3 | 4 | 7
1 | C | 3
0 |  | 0
1 | 2 | 3
8 | H | 9
0 |  | 0
8 | 1 | 9
6 | F | 7
1 |  | 1
7 | 1 | 8
7 | G | 8
0 |  | 0
7 | 1 | 8
(A)Reserve a Server in Google cloud | (B)gathering info from the ministry health and hospital | (C) Design | (D) Develop
(E) Coding | (F) Test coding | (G) Test Develops | (H) Full Test
Network

## Slide 9
 | RS | DUR | ES | LF | SL | 0 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15
A | 1 | 1 | 0 | 1 | 0 | reserve server in Google cloud | 1 |  |  |  |  |  |  |  |  |  |  |  |  |  | 
B | 2 | 1 | 0 | 1 | 0 | gathering information | 2 |  |  |  |  |  |  |  |  |  |  |  |  |  | 
C | 2 | 2 | 1 | 3 | 0 | design |  | 2 | 2 |  |  |  |  |  |  |  |  |  |  |  | 
E | 3 | 5 | 8 | 13 | 0 | coding |  |  |  |  |  |  |  |  | 3 | 3 | 3 | 3 | 3 |  | 
D | 3 | 4 | 3 | 7 | 0 | develop |  |  |  | 3 | 3 | 3 | 3 |  |  |  |  |  |  |  | 
F | 2 | 1 | 13 | 14 | 0 | test(develop) |  |  |  |  |  |  |  |  |  |  |  |  |  | 2 | 
G | 2 | 1 | 7 | 8 | 0 | test(coding) |  |  |  |  |  |  |  | 2 |  |  |  |  |  |  | 
H | 2 | 1 | 14 | 15 | 0 | full test |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 2
 |  |  |  |  |  |  | 3 | 2 | 2 | 3 | 3 | 3 | 3 | 2 | 3 | 3 | 3 | 3 | 3 | 2 | 2
 |  |  |  |  |  |  | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3
Slake Table

## Slide 10
0 | A | 1
0 | 1p | 0
0 | 1 | 1
0 | B | 1
0 | 2p | 0
0 | 1 | 1
8 | E | 13
0 | 3p | 0
8 | 5 | 13
3 | D | 7
0 | 3p | 0
3 | 4 | 7
1 | C | 3
0 | 2p | 0
1 | 2 | 3
14 | H | 15
0 | 2p | 0
14 | 1 | 15
13 | F | 14
0 | 2p | 0
13 | 1 | 14
7 | G | 8
0 | 2p | 0
7 | 1 | 8
(A)Reserve a Server in Google cloud | (B)gathering info from the ministry health and hospital | (C) Design | (D) Develop
(E) Coding | (F) Test coding | (G) Test Develops | (H) Full Test
Edited Network

## Slide 11
 | DUR | 0 | BUDJET X 1000$ | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15
A | 1 | reserve server in Google cloud | 13 | 13 |  |  |  |  |  |  |  |  |  |  |  |  |  | 
B | 1 | gathering information | 2.5 | 2.5 |  |  |  |  |  |  |  |  |  |  |  |  |  | 
C | 2 | design | 10 |  | 5 | 5 |  |  |  |  |  |  |  |  |  |  |  | 
E | 5 | coding | 40 |  |  |  |  |  |  |  |  | 5 | 10 | 10 | 10 | 5 |  | 
D | 4 | develop | 30 |  |  |  | 5 | 10 | 10 | 5 |  |  |  |  |  |  |  | 
F | 1 | test(coding) | 1.5 |  |  |  |  |  |  |  |  |  |  |  |  |  | 1.5 | 
G | 1 | test(develop) | 1 |  |  |  |  |  |  |  | 1 |  |  |  |  |  |  | 
H | 1 | full test | 2 |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 2
week total |  |  | 100,000 | 15.5 | 5 | 5 | 5 | 10 | 10 | 5 | 1 | 5 | 10 | 10 | 10 | 5 | 1.5 | 2
cumulative |  |  |  | 15.5 | 20.5 | 25.5 | 30.5 | 40.5 | 50.5 | 55.5 | 56.5 | 61.5 | 71.5 | 81.5 | 91.5 | 96.5 | 98 | 100
Budget Table

## Slide 12
Gannt chart
A | reserve server in Google cloud |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
B | gathering information |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
C | design |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
D | develop |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
E | coding |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
F | test(develop) |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
G | test(coding) |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
H | full test |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
 | 0 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15

## Slide 13
R i s k s | risks | 
 | Severity | Description
We are working on a long-term plan for development. | Low | Constantly developing and updating.
We can delay the project until all the resources are complete. | medium | We cannot get the resources in time.
We convince them that we will create an application that will help them solve the problem of blood deficiency and we use some documents that indicate this application. | Medium | Approval of some hospitals due to safety.
We reduce the resource of application. | High | Increase in the cost
We convince them that we will create an application that will help them solve the problem of blood deficiency and we use some documents that indicate this application | High | Approval from the Ministry of Health
Hiring a specialist to review legal papers. | High | Legal Procedures and Licensing (Software Licenses)
We store data on more than one server. | High | Server failures

## Slide 14
Time of the meeting
Every Thursday “online meeting “
Every Tuesday in the college